## Estimation Guidelines
Automation Estimation Guidelines
Test Case Analysis
Complexity Level | # of Functional Test Steps | # of Screen Navigations | # of Validations |  | # of Interface Navigations / Actions |  | Effort [Hrs]
Low [L] | <=5 | <=2 | <=4 |  | 0 |  | 0.2
Medium [M] | >5 and <=10 | >2 and <=4 | >4 and <=6 |  | 1 |  | 0.5
High [H] | >10 and <=20 | >4 and <=6 | >6 and <=10 |  | 2 |  | 0.75
Functions Development
Complexity Level | # of Lines of Code | # of Logincal Operations |  | Effort [Hrs]
Low [L] | <=15 | <=4 |  | 1
Medium [M] | >15 and <=30 | >4 and <=6 |  | 2
High [H] | >30 and <=60 | >6 and <=15 |  | 4
Automation Script Development
Complexity Level | Overall Navigation / Verification Actions/Edit/Click Business Component |  |  | Effort [Hrs]
Low [L] | <=15 |  |  | 6
Medium [M] | >15 and <=30 |  |  | 8
High [H] | >30 and <=60 |  |  | 12
Automation Script Modification
Complexity Level | Overall Navigation / Verification Actions/Edit/Click Business Component |  |  | Effort [Hrs]
Low [L] | <=10 |  |  | 4
Medium [M] | >10 and <=20 |  |  | 6
High [H] | >20 and <=40 |  |  | 10
Automation Script Review
Complexity Level | Overall Navigation / Verification Actions/Edit/Click Business Component |  |  | Effort [Hrs]
Low [L] | <=15 |  |  | 0.5
Medium [M] | >15 and <=30 |  |  | 1
High [H] | >30 and <=60 |  |  | 1.5
Test Data Management
Complexity Level | # of Read/Updates in Datasheet | Effort [Hrs]
Low [L] | <=10 | 0.25
Medium [M] | >10 and <=25 | 0.5
High [H] | >25 and <=40 | 0.75
Test Data Extraction
Complexity Level | # of Tables involved in Query | Effort [Hrs]
Low [L] | <=2 | 0.25
Medium [M] | >2 and <=4 | 0.3
High [H] | >4 and <=7 | 0.75
Automation Script - Dryrun
Activity | Activity Details |  |  | Effort [Hrs]
Dry run | Test Script execution [one time] excluding End-To-End Test Scripts |  |  | 0.5
Test Script Execution
Complexity Level | # of Functional Test Steps | # of Screen Navigations | # of Validations |  | # of Interface Navigations / Actions |  | Effort [Hrs]
Low [L] | <=5 | <=2 | <=4 |  | 0 |  | 0.25
Medium [M] | >5 and <=10 | >2 and <=4 | >4 and <=6 |  | 1 |  | 0.5
High [H] | >10 and <=20 | >4 and <=6 | >6 and <=10 |  | 2 |  | 1
Test Data Preparation
Complexity Level | # of Updates in Datasheet | Effort [Hrs]
Low [L] | <=10 | 0.1
Medium [M] | >10 and <=25 | 0.2
High [H] | >25 and <=40 | 0.25
Complexity Level | # of Verification Points
Low [L] | <= 8 verification points
Medium [M] | > 8 and <= 15 verification points
High [H] | > 15 and <= 20 verification points
Complexity Level | # of Test Steps
Low [L] | <= 7 test steps
Medium [M] | > 7 and <= 12 test steps
High [H] | > 12 and <= 17 test steps
Manual Estimation Guidelines
Test Case Analysis
Complexity Level | # of Functional Test Steps | # of Screen Navigations | # of Interface Navigations / Actions |  |  | Effort [Hrs]
Low [L] | <=5 | <=2 | 0 |  |  | 0.5
Medium [M] | >5 and <=10 | >2 and <=4 | 1 |  |  | 1
High [H] | >10 and <=20 | >4 and <=6 | 2 |  |  | 1.25
Manual Test Case Designing
Complexity Level | Overall Navigations / Steps | Effort [Hrs]
Low [L] | <=15 | 4
Medium [M] | >15 and <=30 | 6
High [H] | >30 and <=60 | 10
Manual Test Case Modification
Complexity Level | Overall Navigation / Steps | Effort [Hrs]
Low [L] | <=10 | 2
Medium [M] | >10 and <=20 | 4
High [H] | >20 and <=40 | 8
Manual Test Case Review
Complexity Level | Overall Navigation / Steps | Effort [Hrs]
Low [L] | <=15 | 1
Medium [M] | >15 and <=30 | 2
High [H] | >30 and <=60 | 3.5
Test Data Management
Complexity Level | # of Data Fields in Datasheet | Effort [Hrs]
Low [L] | <=10 | 0.25
Medium [M] | >10 and <=25 | 0.5
High [H] | >25 and <=40 | 0.75
Note - If, in any situation, the range of verification points exceeds High complexity limit mentioned above, the same needs to be split into L, M, and H for estimation basis.

## Estimates
| Legend | Headings | Input Data | Calculated |  |  | No Resource
[7 empty] | 1 | 14 | 8 | 560
Automation Script Designing | [6 empty] | 2 | 14 | 8 | 1120
[7 empty] | 3 | 14 | 8 | 1680
Reusability % | 10% | [5 empty] | 4 | 14 | 8 | 2240
Contingency | 10% | [5 empty] | 5 | 14 | 8 | 2800
Schedule [# of Fiscal Weeks] | 14 | [5 empty] | 6 | 14 | 8 | 3360
| Complexity wise # of Test Cases |  |  |  | Total | Comments | 7 | 14 | 8 | 3920
| Low | Medium | High | Total | Effort (hrs) |  | 8 | 14 | 8 | 4480
Framework/Functions Designing | 0 | 0 | 0 | 0 | 40 |  | 9 | 14 | 8 | 5040
New Automation Script Designing | 157 | 262 | 105 | 524 | 4298 |  | 9.5 | 14 | 8 | 5320
Script Modification | 0 | 0 | 0 | 0 | 0 |  | 11 | 14 | 8 | 6160
Script Review | 157 | 262 | 105 | 524 | 498 |  | 12 | 14 | 8 | 6720
Test Data Management | 157 | 262 | 105 | 524 | 249 |  | 13 | 14 | 8 | 7280
Test Data Extraction | 0 | 0 | 0 | 0 | 0 |  |  | 14
Dry Run [One Iteration] | 157 | 262 | 105 | 524 | 183.5
Project Coordination | 1 | hrs/day |  |  | 70 | Calculated based on the schedule [#of fiscal weeks] above
Functional Team Support / Issue Clarification | 1 | hrs/day |  |  | 70 | Calculated based on the schedule [#of fiscal weeks] above
Total Efforts [minus Reusability] with Contingency |  |  |  |  | 5421.79 | Considered "Reusability %" and added "Buffer"
|  |  |  | Days | 678 | 32.2857
Automation Execution
Unmonitored Execution % | 20%
Defect Injection | 10%
Contingency | 10%
Schedule [# of Fiscal Weeks] | 2
| Complexity wise # of Test Cases |  |  |  | Total | Comments
| Low | Medium | High | Total | Effort (hrs)
Test Data Preparation | 341 | 265 | 151 | 757 | 124.85
Script Execution | 341 | 265 | 151 | 757 | 295 | Excludes unmonitored execution time
Failed Script Analysis & Re-execution | 34.1 | 26.5 | 15.1 | 75.7 | 36.875
Project Coordination | 1.25 | hrs/day |  |  | 12.5
Functional Team Support / Issue Clarification | 0.75 | hrs/day |  |  | 7.5
Defect Logging | 0.25 | hrs/defect |  |  | 19
Total Efforts |  |  |  |  | 495.725
Total Efforts with Contingency |  |  |  |  | 545.2975
13.6324
[5 empty] | 81326.85 | 113857.59
|  |  |  | Func Cons | 40320 | 40320
Assumption : |  |  |  | Load runner | 10080 | 10080
These are the Ballpark estimations and it may warry in actual |  |  |  | Test Manager | 10080 | 10080
|  |  |  | ALM | 20160 | 20160
|  |  |  | Devops | 10080 | 10080
[5 empty] | 172046.85 | 204577.59
240865.59

## Sheet1
Buffer 50%
|  | Total | 523 |  | 261.5 | 784.5 | 20 | 50 | 30
| Alpha TCS and TX CM&U |  | 207 |  |  |  | 30 | 40 | 30
| Parts regression |  | 40
| APEX |  | 100
| GL COE |  | 25 |  |  |  | 105 | 262 | 157
| Collection&Cash Mgmt |  | 116 |  |  |  | 157 | 209 | 157
| Finance Scenarios_NO3 |  | 35
Team Size
Alpha MGPP UpLift | CS E2E | 1 | 93 | 2 | 2
Alpha MGPP UpLift | TX CM&U E2E | 1 | 207 | 2 | 4
Alpha MGPP UpLift | Parts E2E regression | 1 | 12 | 1
Alpha MGPP UpLift | APEX | 1 | 105 | 2
Alpha MGPP UpLift | GL COE | 1 | 5 | 0.5
Alpha MGPP UpLift | Collection | 1 | 59 | 1
Alpha MGPP UpLift | Cash Mgmt | 1 | 57 | 1
Alpha MGPP UpLift | CS E2E Regression | 1 | 75
Alpha MGPP UpLift | Finance Scenarios_NO3 |  | 35 | 0.5

## Schedule
Proposed Project Plan
 | time axis 2022-05-23 to 2022-07-19
Project Intitiation | bar: 2022-05-23 to 2022-05-24
Familiarization & KT | bar: 2022-05-23 to 2022-05-24; 2022-05-27 to 2022-05-30; 2022-06-02 to 2022-06-03
Framework Designing | bar: 2022-05-24 to 2022-05-26
Manual Dry Run/Script Design
Script Review/ Dry Run
Functional Sign-Off | bar: 2022-05-30 to 2022-05-31; 2022-06-06; 2022-06-13; 2022-06-20; 2022-06-27; 2022-07-04; 2022-07-11
Execution Phases